# 2009-10 DRAFT

# April 15, 2009

# College Station

# Independent School District

# DISTRICT IMPROVEMENT PLAN

2009-10

2009-2010 District Improvement Plan

Executive Summary

The District-wide Educational Improvement Council considered a great deal of student performance data and other data as we crafted the new District Improvement Plan (DIP).  The committee looked at the TAKS performance by student group for each subject and compared CSISD scores to overall state scores.  We looked at district and state comparisons for those students passing the test and those students earning commended performance on the tests, as well.

The committee observed that the African American and sometimes the economically disadvantaged student groups did not meet the performance levels of their peers throughout the state.  We also recognized that the subject areas with the greatest potential for improvement were the areas of math and science.

The committee also compared the gaps between white student performance and other student groups (African American, Hispanic and economically disadvantaged) for the past two years.  The goal was for the performance gap between white students and the other student groups to decrease in 2008 when compared to 2007.  While the gaps did decrease in some areas, the committee felt that this was still an area for improvement.

Another major focus of the DIP is ensuring that all student groups are not over-represented or under-represented in many of our educational programs.  To that end we looked at the percentage of students in each student group: (1) in advanced courses, (2) nominated for gifted and talented testing, and (3) referred for and receiving special education services.  Improvement was made in both G/T nominations and the percentage of African American students being referred for special education services.  The committee did feel that the district still needs to make improvement in these areas, so they were included in the 2009-10 DIP.

- AVID

  - Goal 1  Academic Success:  	    		Objective  C3, D2

  - Goal 2  Unique Needs: 	   		Objective  A1,E2

  - Goal 3  Scientific Research: 	    		Objective  B4

  - Goal 4	Parent and Community:		Objective  C4

- Achieve Texas

- Goal 1  Academic Success:   			Objective  E1

  - Goal 4  Parents and Community:  		Objective  C3

- Campus Improvement Planning

  - Goal 1 Academic Success			Objective B2

- Cognitive Tutor

  - Goal 1 Academic Success			Objective C5

- Communication

  - Goal 4	Parents and Community:		Objective  B1, E1, E2

- Coordinated Behavior Management Plan

  - Goal 5	 Safe, Supportive Environment:	Objective B1, B2, B3, B4,  C1, C2

- Curriculum Alignment

  - Goal 1  Academic Success:			Objective  A4

  - Goal 3  Scientific Research:			Objective  A1, A2

- Differential Staffing

  - Goal 1 Academic Success			Objective C1

- Dropout Prevention

  - Goal 1  Academic Success:			Objective  A3

- Dual Credit

  - Goal 1  Academic Success:			Objective  E5

- Evaluate Student Achievement

  - Goal 1  Academic Success:			Objective  A1

- 4X4 Recommendations

  - Goal 1  Academic Success:			Objective  E6

- Instructional Technology

  - Goal 3  Scientific Research:			Objective  B6

- Long Range Educational Planning

  - Goal 1 Academic Success			Objective B1

- Math Specialists

  - Goal 1  Academic Success:			Objective  B3, C4

  - Goal 2 Unique Needs				Objective C4

- Parents and Outreach Initiatives

  - Goal 1  Academic Success:		Objective  E3

  - Goal 4  Parents and Community:		Objective  A1, A2, A3, B2, B3, C1, D1, D2

- Post-Secondary Transition Awareness

  - Goal 1  Academic Success:			Objective  E2

  - Goal 4  Parents and Community:		Objective  C2

- Professional Learning Communities

  - Goal 1  Academic Success:			Objective A5, B4, D1

  - Goal 2  Unique Needs:			Objective E1

  - Goal 3  Scientific Research:			Objective B3

- Response To Intervention (RTI)

  - Goal 1	Academic Success:			Objective  A7, C2

  - Goal 2	Unique Needs:				Objective  C2, C3

  - Goal 3	Scientific Research:			Objective  B5

- School Health Program

  - Goal 2  Unique Needs:	    		Objective  D1

- School Safety

  - Goal 5  Safe, Supportive Environment:	Objective A1, A2, A3

- Staff Development for ESL/Bilingual

  - Goal 3  Scientific Research:			Objective  B6

- Ten Components of School-wide Campus

  - Goal 1  Academic Success:			Objective  A6

- Universal Screening

  - Goal 1  Academic Success:			Objective A2

  - Goal 2  Unique Needs:			Objective C1

Goal 1:  All Students Will Achieve Academic Success

Objective A:  All students will pass the Texas Assessment of Knowledge and Skills in 2009-10.

| Goal 1 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| A1 | The district will evaluate student achievement in the following programs: Title I, Bilingual/ESL, LEP, Gifted and Talented, Special Education, Career and Technology Education and students in at risk situations | - Exec Director for Accountability and Planning - C&I Directors | Staff Time | Completed by October 2009 | Programs evaluated and analyzed and all students pass the TAKS. |
| A2 | Universal screenings of preK-8 students (primarily through the use of AIMSweb®) will identify students at risk. | - Director for Instruction - Principals | $30,000 IDEA $2,000 Head Start EIS/IDEA $10,000 Local | July-June | Universal screenings are administered three times per year in math and reading |
| A3 | The district will provide support for the students at risk of dropping out of school by providing supplemental instruction through instructional resources and staff development resources, including through an alternative education program | - Dir. for Special Programs - Principals | $937,210.39 State Comp Ed Funds to include at least 18.5 teaching units | July-June | Completion rate at 95% or higher, drop out rate for grades 7-8 below 1%, all students pass the state mandated exams |
| A4 | Continue alignment of curriculum to the State standards in the core subject areas with emphasis in Math, Science, ELA. | - Dir. for Curriculum - Deputy Supt for C&I | Staff Time | July- June | Scope and sequence designed and implemented |

Goal 1:  All Students Will Achieve Academic Success

Objective A:  All students will pass the Texas Assessment of Knowledge and Skills in 2009-10.

| Goal 1 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| A5 | Professional Learning Communities at each campus will provide the support structure to align data (e.g., CBM’s, AIMSweb®), curriculum (e.g., Scope and Sequence), and research-based instructional strategies (e.g., Schlechty, EEI, RTI, AVID) with student success. | - Deputy Supt for C&I - Dir. for Curriculum - Dir. for Instruction - Campus Principals - Campus Teachers | -Staff Time | July- June | - Staff development plans reflect team sessions - Student passing rate on 2009-10 TAKS |
| A6 | Title I, Part A campuses will implement the ten components of a school-wide campus to maximize student learning and achievement | - Principals - Academic Coordinators | Title I, Part A Funds $1,000,000 | July- June | Campus Improvement Plans |
| A7 | Research-based interventions and progress monitoring will be provided for students at risk. | - C&I Directors - Principals | - Local funds - State Funds - ARI, AMI Funds - EIS Funds - Title I, III - Staff | July-June | District will track interventions and progress made by at risk students |

Objective Evaluation A: All students will pass the Texas Assessment of Knowledge and Skills in 2009-10.

Goal 1:  All Students Will Achieve Academic Success

Objective B:  In all tested grade levels and subject areas, each African American, Hispanic and economically disadvantaged student group will exceed the state average on TAKS tests in their respective student group.

| Goal 1 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| B1 | Establish a culture of high expectations that is based on the Long Range Educational Planning belief statements. | - Superintendent - Deputy Supt for C&I - Campus Principals | - Title II Funds - Local Funds | July-June | - High expectations reflected in Campus and District Improvement Plans |
| B2 | Each campus principal will develop a clear and compelling academic/instructional focus based on campus needs identified through the Campus Improvement Plan process | - Exec Director for Accountability and Planning - Deputy Supt for C&I - Campus Principals | Staff Time | July-June | - Planning documents will reflect the principal’s map for student success |
| B3 | Continue to provide math specialists for identified K-6 students at-risk of not performing on grade level | - Deputy Supt for C&I - C&I Directors - Principals | $200,000 Local Funds | August 2009 | - Math specialists employed and interventions implemented |
| B4 | Professional Learning Communities at each campus will provide the support structure to align data (e.g., CBM’s, AIMSweb®), curriculum (e.g., Scope and Sequence), and research-based instructional strategies (e.g., Schlechty, EEI, RTI, AVID) with student success. | - Dir. for Curriculum - Dir. for Instruction - Deputy Supt for C&I - Campus Principals - Campus Teachers | -Staff Time | July- June | - Staff development plans reflect team sessions - Student passing rate on 2009-10 TAKS |

Objective Evaluation B: - The percentage of African American, Hispanic and economically disadvantaged students passing the TAKS tests in all subjects will exceed the state average in their respective student groups.

# Goal 1:  All Students Will Achieve Academic Success

Objective C:  Student TAKS performance will reflect a reduced achievement gap.

| Goal 1 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| C1 | Differential staffing will be provided at two elementary Title I campuses to reduce the student-to-teacher ratio | - Superintendent - Deputy Supt for C&I - Campus Principals | -Title I Funds - Local Funds | July- June | - Student to teacher ratios will be reduced - Student passing rates on 2009-10 TAKS |
| C2 | Research-proven interventions and progress monitoring will be provided for students at risk. | - C&I Directors - Principals | Local funds Staff | July-June | District will track interventions and progress made by at-risk students |
| C3 | Expand AVID to grade 12. AVID is currently established in grades 6-11. | - Deputy Supt for C&I - Dir. for Curriculum - Intermediate, Middle and High School Principals | - 2 FTE - $78,950 High School Allotment funds | July-Dec | - AVID implemented in grades 6-12 |
| C4 | Continue to provide math specialists for identified K-6 students at risk of not performing on grade level | - Deputy Supt for C&I - C&I Directors - Principals | $200,000 Local Funds | August 2008 | - Math specialists employed and interventions implemented |
| C5 | Expand Cognitive Tutor® to grades 7, 8, Algebra II, and Geometry. Cognitive Tutor® classes are currently offered in Algebra I. | -Dir. for Curriculum | TBD | July-June | -Cognitive Tutor established for identified courses. |

Objective Evaluation C: Reduce the achievement gap between white students and African American, Hispanic, and economically disadvantaged students by 10% (not percentage points).

# Goal 1:  All Students Will Achieve Academic Success

Objective D:  Commended Performance will exceed the State average.

| Goal 1 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| D1 | Professional Learning Communities at each campus will provide the support structure to align data (e.g., CBM’s, AIMSweb®), curriculum (e.g., Scope and Sequence), and research-based instructional strategies (e.g., Schlechty, EEI, RTI, AVID) with student success. | - Dir. for Curriculum - Dir. for Instruction - Deputy Supt for C&I - Campus Principals - Campus Teachers | -Staff Time | July- June | - Staff development plans reflect team sessions - Student passing rate on 2009-10 TAKS |
| D2 | Expand AVID to grade 12. AVID is currently established in grades 6-11. | - Deputy Supt for C&I - Dir. for Curriculum - Intermediate, Middle and High School Principals | - 2 FTE - $78,950 High School Allotment funds | July-Dec | - AVID implemented in grades 6-12 |

Objective Evaluation D: The percentage of all students and all student groups achieving commended performance on the TAKS tests in all subjects will exceed the state average in their respective student groups.

# Goal 1:  All Students Will Achieve Academic Success

Objective E:  The district will provide higher education and career/technology education preparation and awareness

for all students.

| Goal 1 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| E1 | Continue to research and develop a plan for implementation of Achieve Texas | - Director for CATE - Dir of Admn Services - Counselors | Staff Time | July-June | Document which reflects a plan for Achieve Texas |
| E2 | Continue to enlist local businesses to recruit students and support post- secondary transition awareness for special education students | - Dir of Public Relations - Dir of Special Svcs - VAC teachers - SpEd Dept Head - Transition Coordinator | Staff Time | July-June | List of new businesses who support Sp Ed students as employees |
| E3 | Continue collaboration with the TAMU Early Outreach program to identify and recruit students for post secondary education | - Dir. of Admn Services | Staff Time | July-June | - Students recruited to attend post secondary education - Campus Guidance Plans - CATE Handbook |
| E4 | The district will provide information regarding curriculum choices that prepare students for success beyond high school, including colleges, universities and technical schools | - Dir. for CATE - Dir. of Admn Services - AVID teachers - Counselors - Principals | Staff Time | July-June | Counseling Guidance Plans; Transition Plans; CATE Handbook; Counselor Handbook; Course Selection Guide |
| E5 | Continue to offer 18 hours of Dual Credit and a strong Advanced Placement program for high school students | - Deputy Supt for C&I - High School Principal | Staff Time | July-Dec | Dual Credit Program established |
| E6 | Continue to implement the 4X4 recommendations of providing selected high school credits (including Spanish II) at the middle school level | - Deputy Supt for C&I - Middle School Principals | 2 FTE | August 2008 | Classes offered in the course description guide and students enrolled |

Goal 2:  Educational Opportunities Will Meet the Unique Academic, Social and Emotional Needs of All Students

Objective A:  The percentage of African American, Hispanic, and economically disadvantaged students enrolled in

advanced classes will be representative of the CSISD school population.

| Goal 2 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| A1 | Expand AVID to grade 12. AVID is currently established in grades 6-11. | - Deputy Supt for C&I - Dir. for Curriculum - Intermediate, Middle and High School Principals | - 2 FTE - $78,950 High School Allotment funds | July-Dec | - AVID implemented in grades 6-12 |
| A2 | Fifth through eleventh grade African American, Hispanic and economically disadvantaged students will be identified, encouraged and counseled to participate in advanced courses | - Dir of Admn Services - Counselors - Principals | Staff Time | August-January | - A list of students who are counseled to take advanced courses - Representative Group of students in advanced classes |
| A3 | Parents of 5-12 African American, Hispanic and economically disadvantaged students identified as candidates for advanced courses will be personally contacted | - Dir. of Admn Services - Dir. of Special Programs - Counselors - Principals | Staff Time | July-December | - A list of parents contacted for their children to take advanced courses - Representative Group of students in advanced classes |

Objective Evaluation A: Increase the proportion of African American, Hispanic, and economically disadvantaged students enrolled in advanced classes by 10% .

Goal 2:  Educational Opportunities Will Meet the Unique Academic, Social and Emotional Needs of All Students

Objective B:  Students nominated for Gifted and Talented/Enrichment will be representative of the CSISD student population.

| Goal 2 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| B1 | Explore options for including underrepresented student groups in activities leading to enrichment & G/T opportunities including AVID at the elementary level. | - Dir. for Special Programs - Dir. for Cuuriculum | $10,000 Local Funds | July-January | - Increased representation of student groups participating in enrichment activities. |
| B2 | K-6 campuses will include training on identification of diverse populations (such as LEP, special education, low SES, and African American & Hispanic students) for gifted and talented services as part of teacher 6 hour annual update | - Dir. of Special Programs - Enrichment Specialists - Principals | Staff Time | July-December | - Staff development agendas will be sent to the Director of Special Programs by January 5, 2010 |

Objective Evaluation B: Increase the percentage of African American and Hispanic G/T nominated students by 2 percentage points.

Goal 2:  Educational Opportunities Will Meet the Unique Academic, Social and Emotional Needs of All Students

Objective C:	Students identified for special education will be representative of the CSISD student population.

| Goal 2 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| C1 | Universal screenings (preK-8 students) will identify students at risk. | - Dir. for Instruction - Principals | - $30,000 EIS - $10,000 Local | July-June | Universal screenings are administered three times per year in math and reading |
| C2 | Provide staff development for teachers that focuses on the intervention strategies for diverse learners | - C&I Directors - Principals | - Bilingual/ESL Allotment - Title II, III funds - IDEA Part B funds | July-June | - Staff development provided - Sp Ed referrals as a percentage of enrollment will decrease |
| C3 | Research-based interventions and progress monitoring will be provided for students at risk. | - C&I Directors - Principals | - Local funds - Staff - Title I, III - State funds - EIS funds | July-June | - District will track interventions and progress made by at risk students - Sp Ed referrals as a percentage of enrollment will decrease |
| C4 | Continue to provide math specialists for identified K-6 students at risk of not performing on grade level | - Deputy Supt for C&I - C&I Directors - Principals | $200,000 Local Funds | August 2009 | - Math specialists employed and interventions implemented |
| C5 | Expand Special Services program options at selected campuses to maintain feeder patterns where appropriate. | - Dir of Special Services | TBD | July-June | - Selected Special Services programs are expanded in feeder patterns |

Objective Evaluation C: Reduce the percentage of African American students in special education to below 30%.

Goal 2:  Educational Opportunities Will Meet the Unique Academic, Social and Emotional Needs of All Students

Objective D:	A Coordinated School Health Program will be implemented by child nutrition services, physical education teachers,

classroom teachers, nurses, counselors, and family facilitators.

| Goal 2 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| D1 | Staff Development for the TEA approved CATCH (Coordinated Approach To Child Health) will be provided for elementary and intermediate PE teachers. | - Dir. for Curriculum - Dir. of Admn Svcs - Dir. for Child Nutrition - Deputy Supt for C&I | $1,500 Local | August – May | - Program Implemented - Status report presented to the School Health Education Council |
| D2 | Continue AED & CPR training for each campus | - Dir of Admn Services | TBD | July-June | - Record of trainings submitted to Dir. of Admn Services |

Objective E:  Opportunities for dialogue and discussion will be created among teachers and administrators regarding the role that relationships, expectations and school culture play in student performance and behavior.

| Goal 2 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| E1 | Professional Learning Communities at each campus will provide the support structure to align data (e.g., CBM’s, AIMSweb®), curriculum (e.g., Scope and Sequence), and research-based instructional strategies (e.g., Schlechty, EEI, RTI, AVID) with student success. | - Dir. for Curriculum - Dir. for Instruction - Deputy Supt for C&I - Campus Principals - Campus Teachers/Specialists | -Staff Time | July- June | - Staff development plans reflect team sessions - Student passing rate on 2009-10 TAKS |
| E2 | Expand AVID to grade 12. AVID is currently established in grades 6-11 | - Deputy Supt for C&I - Dir. for Curriculum - Intermediate, Middle and HS Princ’s | - 2 FTE - $78,950 HS Allotment funds | July-Dec | - AVID implemented in grades 6-12 |
| E3 | Leadership Skills Academy established for new and aspiring administrators | - Superintendent | TBD | July-June | - Leadership Skills Academy implemented |

Goal 3:  Educational Practices Will Be Predicated on Scientifically Based Research

Objective A:  Monitor, review, and align curricula to meet TEKS standards.

| Goal 3 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| A1 | Continue alignment of curriculum to the State standards in the core subject areas with emphasis in Math, Science, ELA. | - Dir. for Curriculum - Campus Principals | $24,000 Title II Funds | July-June | - Vertical and horizontal teacher groups meet and curricula revised - Curricula based on State standards |
| A2 | Provide opportunities for teachers for summer curriculum & staff development | - Deputy Supt for C&I - C&I Directors | - Title II, III - District comp Time | July-June | - Summer sessions conducted |

Objective B:  Instructional strategies will be used so that students are engaged in learning at all levels.

| Goal 3 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| B1 | Develop a process which assures that curricular materials purchased in 2009-10 and beyond meet scientifically-based research requirements | - Dir. for Curriculum - C&I Directors | Staff Time | July- June | A Process is developed which assures that curricular materials purchased in 2009-10 and beyond meet scientifically-based research requirements |
| B3 | Professional Learning Communities at each campus will provide the support structure to align data, curriculum, and instruction with student success. | - Dir. for Curriculum - Dir. for Instruction - Deputy Supt for C&I - Campus Principals - Campus Teachers | -Staff Time | July- June | - Staff development plans reflect team sessions - Student passing rate on 2009-10 TAKS |
| B4 | Expand AVID to grade 12. AVID is currently established in grades 6-11. | - Deputy Supt for C&I - Dir. for Curriculum - Intermediate, Middle and High School Principals | - 2 FTE - $78,950 High School Allotment funds | July-Dec | - AVID implemented in grades 6-12 |

Goal 3:  Educational Practices Will Be Predicated on Scientifically Based Research

Objective B:  Instructional strategies will be used so that students are engaged in learning at all levels.

| Goal 3 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| B5 | Research-based interventions and progress monitoring will be provided for students at risk. | - C&I Directors - Principals | - Local funds - Staff - Title I, III - State funds - EIS funds | July-June | District will track interventions and progress made by at risk students - Sp Ed referrals as a percentage of enrollment will decrease |
| B6 | Staff development for all ESL/Bilingual certified teachers will be available | - Dir. for Special Programs | - Bilingual/ ESL allotment - Title III Funds | July-June | - Training provided - Meet AMAO’s |
| B7 | Provide technology training for teachers that focuses on engaging students by enabling them to integrate technology into student products | - Deputy Supt for C&I - Technology Specialists | $8,000 Local funds Title II Funds | July-June | Technology training provided and lessons integrated |
| B8 | Provide staff development for teachers that focuses on the instruction strategies for diverse learners. | - Dir. for Special Programs | TBD | July-June | Staff development sessions are provided |

Goal 4:  Parents and Community Members Will Be Actively Engaged

Objective A:  Parental involvement will be representative of the CSISD student population.

| Goal 4 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| A1 | Campuses will continue outreach initiatives through community centers (such as the Lincoln Center, Windsor Pointe and the Barbara Bush Parent Center) to partner with parents and community members | - Principals - Dept Supt for C&I | Staff Time | July-June | - Events scheduled at community centers - Parent and community member attendance at events |
| A2 | African American, Hispanic and economically disadvantaged parents and community members will be recruited to participate in CSISD schools activities | - DEIC - Principals - Deputy Supt for C&I | Staff Time | July-June | Identified leaders actively participate in CSISD Schools |
| A3 | Campus and District Improvement Committees will be representative of district demographics | - Principals - Deputy Supt for C&I | Staff Time | July-June | Committee membership represents school demographics |

Goal 4:  Parents and Community Members Will Be Actively Engaged

Objective B:  Training and resources for parents and volunteers will be provided at all campuses.

| Goal 4 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| B1 | Improve parent communication about the availability of online programs such as Parent Internet Viewer to monitor student progress | - Dir. of Public Relations - Principals | Staff Time | July-June | - Evidence of communications to parents via web, hardcopy, and similar items - Increased parent use of online programs such as Parent Internet Viewer |
| B2 | Campuses will continue outreach initiatives through community centers (such as the Lincoln Center, Windsor Pointe and the Barbara Bush Parent Center) to partner with parents and community members | - Principals - Deputy Supt for C&I | Staff Time | July-June | - Events scheduled at community centers - Parent and community member attendance at events |
| B3 | Training will be provided to parents that will better enable them to support their children’s school success to include the areas of TAKS reading, writing, math, social studies and/or science | - Parent Involvement Specialist - Principals | Title I ($10,000) | July-June | Training sessions conducted at multiple places within CSISD |

Goal 4:  Parents and Community Members Will Be Actively Engaged

Objective C:	Parents will be informed of career and higher education opportunities for their children.

| Goal 4 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| C1 | Campuses will continue outreach initiatives through community centers (such as the Lincoln Center, Windsor Pointe and the Barbara Bush Parent Center) to partner with parents and community members | - Principals - Deputy Supt for C&I | Staff Time | July-June | - Events scheduled at community centers - Parent and community member attendance at events |
| C2 | Enlist local businesses to recruit students and support post- secondary transition awareness for special education students | - Dir. of Public Relations - Dir. of Special Services -VAC teachers - HS Sp Ed Dept. Head - Transition Coordinator | Staff Time | July-June | List of businesses who support Sp Ed students as employees |
| C3 | Continue to research and develop a plan for implementation of Achieve Texas | - Dir. for Admn Services - Dir. for CATE - Counselors | Staff Time | July-June | Document which reflects a plan for Achieve Texas |
| C4 | Expand AVID to grade 12. AVID is currently established in grades 6-11. | - Deputy Supt for C&I - Dir. for Curriculum - Intermediate, Middle and High School Principals | - 2 FTE - $78,950 High School Allotment funds | July-Dec | - AVID implemented in grades 6-12 |

Goal 4:  Parents and Community Members Will Be Actively Engaged

Objective D:  Community members will be used as a resource for educational opportunities.

| Goal 4 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| D1 | Campuses will continue outreach initiatives through community centers (such as the Lincoln Center, Windsor Pointe and the Barbara Bush Parent Center) to partner with parents and community members | - Principals - Deputy Supt for C&I | Staff Time | July-June | - Events scheduled at community centers - Parent and community member attendance at events |
| D2 | CSISD will partner with local businesses, community members and parents to support the educational efforts of CSISD schools through programming and donations | - Dir. of Public Relations | $5,000 Local | July-June | Partnerships established with businesses, community members and parents |

Objective E:  Communication strategies will engage community members to learn about the district’s strengths and challenges.

| Goal 4 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| E1 | The district web site will be used for listserv e-mail service to actively communicate with parents and community members | - Dir. of Public Relations | Staff time | June – July | Listserv service established and used by parents and community |
| E2 | Refine the district Communication Plan which specifies the strategies to convey the strengths, challenges, and vision for CSISD | - Dir. of Public Relations | Staff time | June - July | A district Communication Plan will be refined and distributed |

Goal 5:  A Safe and Supportive Environment Will Be Provided For All Students

Objective A:  Each campus will comply with the District Crisis Management Plan.

| Goal 5 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| A1 | The district will continue to update the district crisis management plan to comply with NIMS (National Incident Management System) guidelines | - Exec Director for Accountability and Planning | Staff Time | July-June | Guidelines followed as necessary |
| A2 | Each campus safety team will review and change (if needed) its Crisis Management Plan at least annually | - Exec Director for Accountability and Planning - Principals | Staff Time | July-June | Management plans followed as necessary |
| A3 | Review Safety Audit recommendations and implement as appropriate | - Exec Director for Accountability and Planning | Staff Time | July-June | Safety Audit strategies are implemented as appropriate such as Raptor, locked/secure classroom doors, etc. |

Objective B:  Procedures for management of student behavior will be consistent across the district.

| Goal 5 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| B1 | The district will review data at the end of the year based on types of offenses, intervention, gender and ethnicity in the following areas: number of suspensions, reasons for suspensions, number of discipline referrals, number of expulsions, reasons for expulsions, number of placements at Venture Center, reasons for placements at Venture Center, number of placements in the LEAP program, reasons for placements in the LEAP program, and number of physical restraints | - Exec Director for Accountability and Planning | Staff Time | September 1, 2009 | District discipline referrals decrease from the 08-09 school year |

Goal 5:  A Safe and Supportive Environment Will Be Provided For All Students

Objective B:  Procedures for management of student behavior will be consistent across the district.

| Goal 5 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| B2 | CSISD will be consistent in applying disciplinary consequences at all levels | - Dir. for Admn Services | Staff Time | July-June | Discipline reported in a consistent manner |
| B3 | Continue to develop and/or implement proactive intervention strategies (such as Conscious Discipline©, Boys Town©, etc.) in order to reduce the number of discipline referrals | - Dir. for Instruction - Dir. of Special Svcs - Coor of Special Svcs | Staff Time | July-June | Pre-intervention strategies defined and implemented |
| B4 | Develop and/or implement proactive intervention strategies that address offenses such as bullying, harassment, and violence (dating and/or sexual) | - Dir. for Admn Services | Staff Time Staff Development | July-June | Pre-intervention strategies defined and implemented |

Goal 5:  A Safe and Supportive Environment Will Be Provided For All Students

Objective C:  Behavior management plans will serve the needs of all students.

| Goal 5 | Activity | Person Responsible | Resource/Cost | Time Frame | Evaluation |
| --- | --- | --- | --- | --- | --- |
| C1 | Staff development will be provided on the relationship between student behavior and staff understanding of social, cultural and developmental differences | - Deputy Supt for C&I - Principals | $5,000 Local Funds | July-June | - Staff development provided - Discipline referrals are representative of the CSISD student population |
| C2 | Each campus principal will review discipline data and develop a plan to appropriately address campus discipline issues based on campus needs. | - Exec Director for Accountability and Planning - Deputy Supt for C&I - Dir. of Admn Services - Principals | Staff time | July-June | - Plans developed. - Discipline referrals are representative of the CSISD student population |